## Epic Summary
Jira Epic Plan: Autonomous SRE Agent Architecture via MCP
High-level strategic roadmap and foundational mapping for execution tracking.
Epic Key | SRE-EPIC-001
Epic Title | Implementation of Multi-Agent Autonomous SRE Platform via MCP Gateway
Description | Deploy a modular, multi-agent autonomous engineering platform utilizing an MCP Gateway, domain-specific AI brains, tiered memory architectures, and strict human-in-the-loop (HITL) safety governance to reduce core infrastructure MTTR.
Target Architecture Components | Orchestration Layer, MCP Gateway Bus (Data & Action Routers), External Agent Federation (A2A), Domain Brains (Compute, Network, Storage, Platform), Memory Tier (Redis, VectorDB, PostgreSQL), Operator Hands, Execution Validation.
Business Value / Impact | Transforms traditional passive monitoring into actively governed, validated, and self-healing automation loops, dramatically minimizing human on-call fatigue and maximizing operational uptime.

## Jira Backlog
Issue Key | Issue Type | Summary | Sprint/Phase | Epic Link | User Story Description (As a... I want... So that...) | Acceptance Criteria | Priority | Status
SRE-1 | Story | Implement MCP Ingestion & Data Router Gateway | Sprint 1 | SRE-EPIC-001 | As an Orchestrator Node, I want a unified Model Context Protocol (MCP) data bus to ingest telemetry from Datadog/Prometheus, ACM, GitOps APIs, and Service Mesh Topologies, So that all system telemetry is standardized and routed to the central orchestration engine. | 1. Build an MCP Gateway server capable of handling webhook payloads from Prometheus/Datadog. 2. Contextually aggregate topology and GitOps state into a unified payload wrapper. 3. Route standardized payloads to the Orchestrator Node within defined SLA limits (<500ms). | Highest | Ready
SRE-2 | Story | Core Orchestrator & Split-Memory Hierarchy Setup | Sprint 1 | SRE-EPIC-001 | As an SRE System Engineer, I want to implement the core Orchestration node and establish the split-memory hierarchy (Episodic Redis, Semantic VectorDB, Config PostgreSQL), So that the system can track active execution state, pull historical RAG context, and adhere to strict safety boundaries. | 1. Episodic: Configure Redis to store active session tokens, alert IDs, and state transitions. 2. Semantic: Spin up a Vector DB (e.g., PGVector/Qdrant) to hold past postmortems and documentation embeddings. 3. Config: Spin up PostgreSQL with schemas for RBAC roles, execution boundaries, and safety guardrails. 4. Orchestrator node successfully stores state in Redis and boots up on an alert event. | High | To Do
SRE-3 | Story | External Agent Federation via A2A Gateway | Sprint 2 | SRE-EPIC-001 | As an Orchestrator Node, I want an Agent-to-Agent (A2A) adapter protocol to interface with external legacy systems (Cortex Ops Agent), So that I can enrich internal diagnostic data with third-party or existing external system insights. | 1. Implement the A2A Gateway interface capable of sending and receiving JSON schema interactions with Cortex. 2. Reserve an abstract interface/stub class for future plugin integrations. | Medium | To Do
SRE-4 | Story | Core Triage and Ingestion Agent Integration | Sprint 2 | SRE-EPIC-001 | As the SRE Orchestration System, I want a dedicated Triage Agent to rapidly classify incoming data streams prior to heavy domain processing, So that low-latency deduplication and initial priority sorting are handled immediately on the bus. | 1. Classify alert severity and filter out noisy duplicates before invoking heavy LLM reasoning loops. 2. Ensure parsed triage markers are stored within the current Redis session block. | High | To Do
SRE-5 | Story | Deploy Domain-Specific Reasoning Agents (Compute, Network, Storage, Platform) | Sprint 3 | SRE-EPIC-001 | As the Orchestration Layer, I want to distribute parsed incident contexts to specialized LLM Domain Agents (Compute, Network, Storage, Platform) with access to Semantic Memory, So that deep, domain-isolated root-cause analysis can be performed in parallel. | 1. Build separate LLM agent prompts/pipelines customized for Compute (K8s/Pods), Network (OVN/Mesh), Storage (Ceph/OSD), and Platform (Certs/Upgrades). 2. Integrate RAG pipelines linking each Brain to the Semantic VectorDB. 3. Domain agents must return a standardized JSON remediation plan proposal to the orchestrator. | High | To Do
SRE-6 | Story | Build Governance Agent & Human-In-The-Loop (HITL) Gate | Sprint 4 | SRE-EPIC-001 | As an Enterprise Infrastructure Platform, I want proposed actions evaluated by a Governance Agent against Config Memory and routed to an interactive ChatOps platform (Slack/PagerDuty), So that no destructive actions are executed without passing automated safety compliance checks or human verification. | 1. Governance Agent checks remediation against PostgreSQL policies and flags exceptions. 2. System formats proposed plans into an interactive Slack message with 'Approve' and 'Deny' interactive blocks. 3. Denials route the state safely back to the Orchestrator with an audit log. | Highest | To Do
SRE-7 | Story | Implement Deterministic Action Operators & Validation Loop | Sprint 4 | SRE-EPIC-001 | As an Approved Remediation Path, I want to execute deterministic code scripts/operators (Compute, Network, Storage, Platform Hands) and hand over to an Execution Validation Agent, So that real changes are made reliably via API and verified for stability. | 1. Operators: Build target-specific actions (e.g., executing a K8s pod scale via SDK, editing Ceph configurations). 2. Validation Agent: Post-execution, pull live metrics from the MCP Gateway for 5 minutes to track resolution. If anomalies persist, safely roll back or trigger a failure status back to the Orchestrator. | High | To Do
SRE-8 | Story | Auto-Generation of Postmortems via Documentation Agent | Sprint 5 | SRE-EPIC-001 | As an Engineering Team, I want a Documentation Agent to compile the incident timeline, root cause, and remediation steps from Episodic memory upon incident resolution, So that it can automatically append a markdown file back into Semantic Memory for future RAG cycles. | 1. Extract data traces from Redis once Execution Validation returns 'Confirmed Resolved'. 2. Generate a highly detailed Markdown postmortem via LLM. 3. Upsert embeddings of the new document back into the Semantic VectorDB dynamically. | Medium | To Do